## Sheet1
Non-time-critical removal actions (NTCRA) are conducted when a removal action is appropriate and a 6-month planning period is available before activities must begin. A NTCRA may be appropriate at NPL sites when it is important to mitigate risks prior to remedy selection. In non-time-critical removal situations, exposure may not actually be occurring but may have a strong potential to occur. Non-time-critical situations pose imminent threats, but do not pose an immediate threat.
Definition | Information Source
Planning Period: A minimum 6 month planning period
· Time period begins with site discovery | Site Discovery - 300.405 NCP
Spending Limit: $2 million limit | "Statutory Time and Limit" - Section 104 (c) - CERCLA
Implementation Period: Less than 12 month implementation from the initiation of site clean-up activities
· Time period begins with initiation of site activities | "Removal Site Evaluation" - 300.410 NCP
· Investigating and planning activities are not included in the time limitations | "Conducting Non-Time Critical Removal Actions Under
· EE/CA preperation costs are not included in the $2 million limit | CERCLA" EPA/540/F-94/009, December 1993
(exemptions can be obtained if it is determined that an emergency or immediate risk exists)
· Time period and expenditure cap does not apply to PRP lead removals
Entity Conducting NTCRA | Information Source
· OSC or Remedial Project Manager (OSC/RPM) | Response Operations 300.135 of NCP
· State OSC/RPM, if there is a removal cooperative agreement | 40 CFR Subpart O, § 35.6200-6205
· Responsible Party with OSC/RPM oversight
Documents Typically Generated | Information Source
Memorandum to authorize Engineering Evaluation/Cost Analysis (EE/CA)
EE/CA | 300.415(b)(4)(i) of NCP
Action Memorandum
· Primary decision document for a removal response that describes the site history, current activities, | "Action Memorandum Guidance" -
health and environmental threats, proposed actions and costs, and approval documents by EPA authorities | EPA/540/P-90/004
Community relations plan
Written response to public comment on EE/CA | 300.820(a) of NCP
Pollution Reports (POLREPS) | "Removal Response Reporting" -
· Provides periodic documentation of activities for all removal actions | POLREPS and OSC Reports
· May include: | EPA-540/R-94/023
· Source and circumstances of the release
· Identity of Potentially Responsible Parties (PRPs)
· Removal Actions Taken
· Costs incurred
· Impacts and potential impacts of the release
· Located on OSC Web site (provide link)
Final Reports
· A report of the removal action including As-Builts, Drawings, Sampling Results, and Maps
· Final POLREPS may serve as final report
· If non-TCRA is the final action, document activities sufficiently meet completion
State Role(s) in NTCRAs | Information Source
Lead role if a removal cooperative agreement is in place | Pursuant to 40 CFR Subpart O Section 35.6200
Initial request for the NTCRA | "State Participation at Federal Removal Site"
· Many times the State is the first to know of a site through routine inspections or assessment activities | EPA 540-F-96-023
Review Administrative Order on Consent, if one is negotiated
Provide ARARs
· The OSC/RPM shall consider State ARARs to the extent practicable | "Consideration of ARARs During Removal Actions"
Public Involvement | EPA-540-P-91/011
· Community relations | Sections 300.415(m) and 300.820 of NCP
· Develop administrative record (For State lead only) | "Public Participation Guidance for OSCs -
Site Transition (See ASTSWMO paper) | Community Relations and Administrative Record"
· Maintain the integrity of the removal action following its conclusion | PB92-963416
· Should be considered prior to starting a removal
Evaluate if removal will be consistent with final remedial action
· Post Removal Site Controls (PRSCs) are many times the responsibility of the state | "Policy on Post-Removal Site Control"
Enforcement Activities including site access, financial assurance, and long-term reporting (Add to TCRA)
Review and Comment | EPA-540-P-91/011
· Draft Site evaluation/assessment report
· Draft Action Memo
· Post Removal Site Controls (PRSCs)
· Site Workplan if available
· EE/AC
Public Role in NTCRAs
· Participate in Interviews for Community Relations Plan | "Guidance on Conducting Non-Time-Critical Removal
· Comment on EE/CA | Actions Under CERCLA" EPA540-R-93-057
Enforcement Activities
· PRP Search | "Guidance on Conducting Non-Time-Critical Removal
· Special notice letter to PRP- triggers a 60 to 120-day moratorium on EPA conducting removal | Actions Under CERCLA" EPA540-R-93-057
· Administrative Order on Consent or Unilateral Order